## Backlog
OmniMedVault — Product Backlog ¦ Version 1.0 ¦ Generated: 21 May 2026
ID | Epic | Feature / Story | Description | Phase | Priority | MoSCoW | Category | Actor | Subscription | FR Ref | Status | Story Points | Dependencies | Notes | Owner | Sprint / Milestone
OMV-001 | Auth & Identity | OTP phone login — Patient | Patient registers and logs in via phone number + OTP. JWT access token (15 min) + refresh token (30 days) issued. | Phase 1A | P0 – Critical | Must Have | Feature | Patient | Free | FR01 | Backlog |  |  | AWS Cognito. RS256 JWT signing.
OMV-002 | Auth & Identity | OTP phone login — Doctor | Doctor registers and logs in via phone number + OTP. Same Cognito flow as patient but role = DOCTOR. | Phase 1A | P0 – Critical | Must Have | Feature | Doctor | Free | FR11 | Backlog
OMV-003 | Auth & Identity | Role-based access control (RBAC) | Enforce roles: PATIENT, DOCTOR, HOSPITAL_ADMIN, PLATFORM_ADMIN, FAMILY_PROXY. Guards on all protected routes. | Phase 1A | P0 – Critical | Must Have | Technical | All Actors | Free |  | Backlog
OMV-004 | Auth & Identity | Token refresh & logout | POST /auth/token/refresh to renew access token. POST /auth/logout invalidates refresh token. | Phase 1A | P0 – Critical | Must Have | Feature | All Actors | Free |  | Backlog
OMV-005 | Auth & Identity | Aadhaar eKYC — Patient (Optional) | Optional Aadhaar OTP-based identity verification via DigiLocker API during registration. | Phase 1A | P1 – High | Should Have | Feature | Patient | Free | FR01 | Backlog |  |  | DigiLocker API integration needed.
OMV-006 | Auth & Identity | NMC ID verification — Doctor (async) | On doctor registration, async call to NMC public lookup API. Doctor active in 'pending' state immediately; notified when verified. | Phase 1A | P0 – Critical | Must Have | Feature | Doctor | Free | FR11, A14 | Backlog |  |  | NMC API polling. Prescription creation locked until verified.
OMV-007 | Patient Core | Patient profile — create & update | Create profile with: name, DOB, gender, blood group, known allergies, optional ABHA ID. PUT /patients/me. | Phase 1A | P0 – Critical | Must Have | Feature | Patient | Free | FR01 | Backlog |  |  | PII encrypted at column level (AWS KMS + AES-256).
OMV-008 | Patient Core | Document upload — camera scan & file (PDF/image) | Patient uploads documents via camera or file picker. Accepts JPG, PNG, PDF. Virus scan on upload. | Phase 1A | P0 – Critical | Must Have | Feature | Patient | Free | FR02 | Backlog |  | OMV-017 | Stored in S3. Kafka event triggers OCR pipeline.
OMV-009 | Patient Core | Document categorisation — Prescription / Lab Report / Receipt / Other | Patient categorises each uploaded document. System suggests category from OCR output; patient can correct. | Phase 1A | P0 – Critical | Must Have | Feature | Patient | Free | FR03 | Backlog |  | OMV-008, OMV-017
OMV-010 | Patient Core | Medical timeline view | Chronological feed of all patient documents. GET /patients/me/timeline. Paginated. | Phase 1A | P0 – Critical | Must Have | Feature | Patient | Free |  | Backlog
OMV-011 | Patient Core | Search own records — date, doctor, diagnosis, medicine, specialty | Full-text + structured search across patient's own records. Filters: date range, type, doctor, specialty, free text. | Phase 1A | P0 – Critical | Must Have | Feature | Patient | Free | FR05 | Backlog |  | OMV-019 | Powered by OpenSearch. Specialty resolution via common_name lookup.
OMV-012 | Patient Core | Grant doctor access — QR scan or Doctor ID | Patient grants consent to a specific doctor. Methods: QR code scan or manual doctor ID entry. POST /consent. | Phase 1A | P0 – Critical | Must Have | Feature | Patient | Free | FR06 | Backlog
OMV-013 | Patient Core | Revoke doctor access | Patient revokes a previously granted consent. Immediate effect. DELETE /consent/:doctorId. | Phase 1A | P0 – Critical | Must Have | Feature | Patient | Free | FR07 | Backlog |  | OMV-012
OMV-014 | Patient Core | Audit log — who accessed my records | Patient views immutable audit log. Every data read/write recorded. GET /patients/me/audit-log. | Phase 1A | P0 – Critical | Must Have | Compliance | Patient | Free | FR08 | Backlog |  |  | Append-only table. No UPDATE or DELETE ever.
OMV-015 | Patient Core | Download records as PDF | Patient downloads their medical history as a formatted PDF report. | Phase 1A | P1 – High | Must Have | Feature | Patient | Premium | FR09 | Backlog |  |  | PDF generation service needed.
OMV-016 | Patient Core | Emergency QR code | Scannable QR in the app showing blood group, allergies, current active medications. No login required to view. Patient controls content. | Phase 1A | P0 – Critical | Must Have | Feature | Patient | Free | FR10, A15 | Backlog |  |  | Life-safety feature. Static QR image generated and cached.
OMV-017 | OCR Pipeline | OCR extraction — printed prescriptions (English + Hindi) | Google Cloud Vision API processes uploaded prescriptions. Post-processing extracts: date, doctor name, diagnosis, medicine names, dosage. | Phase 1A | P0 – Critical | Must Have | Technical | Patient | Free | FR04 | Backlog |  | OMV-008 | Target: ≥85% accuracy on printed. Indian drug name dictionary (~15K names).
OMV-018 | OCR Pipeline | OCR extraction — handwritten prescriptions | Google Cloud Vision handles Indian handwriting. AWS Textract as fallback for structured forms. | Phase 1A | P0 – Critical | Must Have | Technical | Patient | Free | FR04, A6 | Backlog |  | OMV-017 | Target: ≥70% accuracy on handwritten.
OMV-019 | OCR Pipeline | OCR post-processing — entity extraction & Elasticsearch indexing | NLP post-processing identifies entities (medicine, doctor, diagnosis). Confidence score check. Low-confidence flagged for patient review. Stored in PostgreSQL + Elasticsearch. | Phase 1A | P0 – Critical | Must Have | Technical | Patient | Free | FR04 | Backlog |  | OMV-017 | Kafka event-driven pipeline.
OMV-020 | OCR Pipeline | Doctor specialty extraction from prescription header | OCR parser attempts to extract doctor's specialty from prescription header (e.g., 'MS Ortho'). Matched against medical_specialties table. If confidence ≥75%, sets doctor_specialty_id. | Phase 1A | P1 – High | Should Have | Technical | Patient | Free | FR05 | Backlog |  | OMV-017, OMV-019 | Falls back to null; patient can manually tag specialty.
OMV-021 | OCR Pipeline | Patient review & correction of OCR output | Patient is notified when OCR completes. Can review and correct extracted text/fields in the app. | Phase 1A | P1 – High | Must Have | Feature | Patient | Free | FR04 | Backlog |  | OMV-017
OMV-022 | Search | Search architecture — Elasticsearch indices setup | Create and configure indices: documents, prescriptions, lab_reports, medical_expenses. Field mappings as per design. | Phase 1A | P0 – Critical | Must Have | Technical | All Actors | Free |  | Backlog |  |  | AWS OpenSearch (managed).
OMV-023 | Search | Specialty synonym resolution for search | When specialty filter used (e.g., 'tooth'), resolve via common_name in medical_specialties table to canonical code before querying. | Phase 1A | P1 – High | Must Have | Technical | All Actors | Free | FR05 | Backlog |  | OMV-022
OMV-024 | Search | Access-controlled search — patient can only search own records | Mandatory patient_id filter on every Elasticsearch query. Enforced at application layer AND query DSL. | Phase 1A | P0 – Critical | Must Have | Compliance | Patient | Free |  | Backlog |  | OMV-022 | Defence in depth: dual enforcement.
OMV-025 | Search | Doctor search within consented patient records | Doctor can search records of patients who have granted active consent. Consent check at application layer. | Phase 1A | P0 – Critical | Must Have | Feature | Doctor | Free | FR13 | Backlog |  | OMV-012, OMV-022
OMV-026 | Doctor Features | Doctor registration — pending + verified states | Doctor registers with NMC ID. Immediately active in 'pending' state. Async NMC verification runs in background. | Phase 1A | P0 – Critical | Must Have | Feature | Doctor | Free | FR11 | Backlog |  | OMV-006
OMV-027 | Doctor Features | View consented patient history | Doctor views full medical timeline of a patient who has granted consent. GET /doctors/:id/patients. | Phase 1A | P0 – Critical | Must Have | Feature | Doctor | Free | FR12 | Backlog |  | OMV-012
OMV-028 | Doctor Features | Active medications & allergies summary card | Highlighted summary card at top of patient view showing current active medications and known allergies. | Phase 1A | P0 – Critical | Must Have | Feature | Doctor | Free | FR14 | Backlog |  | OMV-027
OMV-029 | Doctor Features | Create digital prescription — verified doctors only | Verified doctor creates prescription: diagnosis, medicines (name, dose, freq, duration), notes, follow-up date. Generates QR-coded PDF. POST /prescriptions. | Phase 1A | P0 – Critical | Must Have | Feature | Doctor | Free | FR15 | Backlog |  | OMV-006 | Locked until NMC verification complete.
OMV-030 | Doctor Features | Doctor web interface (Next.js) | Full-featured web interface for doctors. Includes patient list, history view, prescription creation. | Phase 1A | P0 – Critical | Must Have | Technical | Doctor | Free | FR16 | Backlog
OMV-031 | Hospital / Institution | Institution registration & doctor onboarding | Hospital/clinic admin registers institution. Onboards their doctors. POST /institutions/register. | Phase 1A | P0 – Critical | Must Have | Feature | Hospital Admin | B2B | FR29 | Backlog
OMV-032 | Hospital / Institution | API key issuance & embeddable JS widget | Institution gets API key + embeddable React/iframe widget to drop into their existing CRM/HIS. GET /institutions/widget-config. | Phase 1A | P0 – Critical | Must Have | Feature | Hospital Admin | B2B | FR30, A17 | Backlog |  | OMV-031 | OAuth2 flow: CRM authenticates doctors via OmniMedVault Auth.
OMV-033 | Hospital / Institution | Hospital usage dashboard — prescriptions, active doctors, patients served | Monthly usage metrics dashboard for hospital admin. FR31. | Phase 1A | P1 – High | Should Have | Feature | Hospital Admin | B2B | FR31 | Backlog |  | OMV-031
OMV-034 | Hospital / Institution | CRM webhook — prescription.created & consent.granted events | Hospital CRM can subscribe to webhooks. Events pushed when doctor creates Rx or patient grants consent. | Phase 1A | P2 – Medium | Could Have | Feature | Hospital Admin | B2B |  | Backlog |  | OMV-032
OMV-035 | Notifications | Push notification — Firebase FCM | Push notifications via Firebase FCM. Events: doctor accessed records, new prescription, OCR complete, consent activity. | Phase 1A | P0 – Critical | Must Have | Technical | All Actors | Free |  | Backlog |  |  | Template-based, multi-language.
OMV-036 | Notifications | SMS notification — AWS SNS / Twilio | SMS fallback for critical events. Used when push not deliverable (app not installed, device offline). | Phase 1A | P0 – Critical | Must Have | Technical | All Actors | Free |  | Backlog
OMV-037 | Notifications | Email notification — AWS SES | Email channel for non-urgent events (account setup confirmation, monthly summaries). | Phase 1A | P2 – Medium | Could Have | Technical | All Actors | Free |  | Backlog
OMV-038 | Notifications | Medication reminders | Patient can set reminders for medications extracted from prescriptions. Push notification at configured times. | Phase 1A | P2 – Medium | Should Have | Feature | Patient | Free |  | Backlog |  | OMV-029
OMV-039 | Infrastructure | Modular monolith — NestJS backend setup | NestJS modular monolith with module boundaries matching future microservices: auth, users, documents, ocr, search, prescriptions, consent, notifications, institutions, nl-query. | Phase 1A | P0 – Critical | Must Have | Technical | Dev Team | N/A | A19 | Backlog |  |  | AWS ECS Fargate deployment. TypeScript.
OMV-040 | Infrastructure | AWS RDS PostgreSQL (Multi-AZ) setup | Primary database. Multi-AZ for HA. Column-level PII encryption. All schema migrations managed via code. | Phase 1A | P0 – Critical | Must Have | Technical | Dev Team | N/A |  | Backlog
OMV-041 | Infrastructure | AWS S3 — document storage with encryption | S3 bucket for patient uploads and generated PDFs. AES-256 SSE with KMS. Pre-signed URLs only. Versioning enabled. | Phase 1A | P0 – Critical | Must Have | Technical | Dev Team | N/A |  | Backlog |  |  | Lifecycle: move to Glacier after 1 year.
OMV-042 | Infrastructure | AWS Cognito — auth & token management | Fully managed OTP + JWT via AWS Cognito. Zero auth code to write or maintain. | Phase 1A | P0 – Critical | Must Have | Technical | Dev Team | N/A |  | Backlog
OMV-043 | Infrastructure | AWS OpenSearch — search index setup | Managed Elasticsearch equivalent. Indices: documents, prescriptions, medical_expenses. | Phase 1A | P0 – Critical | Must Have | Technical | Dev Team | N/A |  | Backlog
OMV-044 | Infrastructure | ElastiCache Redis — session & query cache | Redis for session caching and frequently accessed patient summaries. Reduces DB load ~60%. | Phase 1A | P1 – High | Must Have | Technical | Dev Team | N/A |  | Backlog
OMV-045 | Infrastructure | GitHub Actions CI/CD pipeline | 5-stage pipeline: lint+unit tests → security scans (Snyk, Trivy, secret detection) → Docker build → staging deploy → production blue-green deploy. | Phase 1A | P0 – Critical | Must Have | Technical | Dev Team | N/A |  | Backlog |  |  | ArgoCD for GitOps. Manual approval gate before prod.
OMV-046 | Infrastructure | CloudWatch + Sentry monitoring | AWS CloudWatch for infra metrics. Sentry for application error tracking. Alerting on error rate, latency, disk usage. | Phase 1A | P1 – High | Must Have | Technical | Dev Team | N/A |  | Backlog
OMV-047 | Infrastructure | Medical specialties lookup table — seed data | Seed 22 specialties into medical_specialties table (code, display_name, common_name). Lookup-based, not enum. | Phase 1A | P0 – Critical | Must Have | Technical | Dev Team | N/A |  | Backlog |  | OMV-040
OMV-048 | Infrastructure | Virus/malware scan on document upload | AWS Macie / ClamAV scan every uploaded file before storing in S3. | Phase 1A | P0 – Critical | Must Have | Security | Dev Team | N/A |  | Backlog |  | OMV-041
OMV-049 | Security & Compliance | TLS 1.3 enforcement — transit encryption | All API traffic over TLS 1.3. TLS 1.2 deprecated. Enforced at API Gateway layer. | Phase 1A | P0 – Critical | Must Have | Security | Dev Team | N/A |  | Backlog
OMV-050 | Security & Compliance | PII log scrubbing middleware | Middleware applied to all services to ensure zero PII (phone, name, DOB) in logs. | Phase 1A | P0 – Critical | Must Have | Compliance | Dev Team | N/A |  | Backlog |  |  | DPDPA 2023 requirement.
OMV-051 | Security & Compliance | AWS WAF — OWASP Top 10 protection | AWS WAF blocks common attacks. Rate limiting per IP and per user at API Gateway. | Phase 1A | P0 – Critical | Must Have | Security | Dev Team | N/A |  | Backlog |  |  | AWS Shield Standard for DDoS.
OMV-052 | Security & Compliance | DPDPA 2023 — right to erasure | Patient can request account deletion. Data purged within 30 days. Automated pipeline. | Phase 1A | P1 – High | Must Have | Compliance | Patient | Free |  | Backlog |  |  | Data retained for lifetime + 7 years after deletion request.
OMV-053 | Security & Compliance | DPDPA 2023 — breach notification pipeline | Automated pipeline to notify CERT-In and affected users within 72 hours of a data breach. | Phase 1A | P0 – Critical | Must Have | Compliance | Dev Team | N/A |  | Backlog
OMV-054 | Security & Compliance | Snyk + SonarQube in CI pipeline | Dependency vulnerability scanning (Snyk) and SAST (SonarQube) on every code push. Fail build on critical findings. | Phase 1A | P1 – High | Must Have | Security | Dev Team | N/A |  | Backlog |  | OMV-045
OMV-055 | Security & Compliance | Quarterly penetration testing | External third-party penetration test quarterly. Findings tracked and remediated. | Phase 1A | P1 – High | Should Have | Compliance | Dev Team | N/A |  | Backlog
OMV-056 | Monetisation | Freemium gate — premium feature middleware | Middleware checks patient.subscription_tier on every premium endpoint. Returns HTTP 402 with upgrade_url for free-tier users hitting premium features. | Phase 1A | P1 – High | Must Have | Technical | Patient | N/A |  | Backlog
OMV-057 | Monetisation | Manual invoicing for hospitals (Phase 1) | B2B hospital billing via manual invoice/UPI link. No automated payment system in Phase 1. | Phase 1A | P2 – Medium | Should Have | Feature | Hospital Admin | B2B | A10 | Backlog |  |  | Stripe integration deferred to Phase 2.
OMV-058 | Localisation | i18n framework setup — English + Hindi (Phase 1) | i18next for web; Flutter Intl for mobile. Configured from day 1. Adding a language = adding translation files only. | Phase 1A | P0 – Critical | Must Have | Technical | Dev Team | N/A | A16 | Backlog |  |  | OCR languageHints: ['en', 'hi'].
OMV-059 | Financial Tracking | Receipt OCR parsing — vendor, date, amount, category | Extend OCR pipeline to parse financial data from receipts: vendor name, date, total amount, expense category (Consultation/Medicine/Lab/Imaging/Procedure/IPD/Other). | Phase 1A | P1 – High | Must Have | Feature | Patient | Premium | FR20, A9 | Backlog |  | OMV-017 | Receipt Parser module. Confidence scoring. Low confidence flagged for manual verify.
OMV-060 | Financial Tracking | Basic receipt parsing (amount + date) — Free tier | Free users get basic amount + date extraction from receipts. Seeds data for premium upgrade. | Phase 1A | P1 – High | Must Have | Feature | Patient | Free |  | Backlog |  | OMV-059 | Freemium hook — free data seeds premium value.
OMV-061 | Financial Tracking | Illness episode creation & document linking | Patient creates an illness episode (title, date range, status). System suggests documents from that period. Patient confirms or manually links. | Phase 1A | P1 – High | Must Have | Feature | Patient | Premium | FR21 | Backlog |  | OMV-059 | One document belongs to one episode only (no double-counting).
OMV-062 | Financial Tracking | Episode expense summary — category breakdown | Total spend per episode broken down by: pre-hospitalisation, IPD, post-hospitalisation, OPD, medicines, consultations. | Phase 1A | P1 – High | Must Have | Feature | Patient | Premium | FR22 | Backlog |  | OMV-061
OMV-063 | Financial Tracking | Ad-hoc financial queries — annual / category / specialty filters | Patient queries: total spend last 12 months, by category (pie chart), by month (bar chart), by specialty (dental, cardiac etc.), by family member. | Phase 1A | P1 – High | Must Have | Feature | Patient | Premium | FR23 | Backlog |  | OMV-059, OMV-043 | Pre-built query cards in 'My Expenses' section.
OMV-064 | Financial Tracking | PDF expense report — episode & annual | Episode Report: itemized receipts, category subtotals, linked Rx/lab reports. Annual Report: all spend in year, breakdown by month/category/family member. | Phase 1A | P1 – High | Must Have | Feature | Patient | Premium | FR24 | Backlog |  | OMV-062, OMV-063 | For insurance claims, employer reimbursement, tax records.
OMV-065 | AI Health Insights | CDSCO regulatory review — SaMD classification | Engage CDSCO healthcare regulatory lawyer to determine if AI health insights require SaMD registration under MDR 2017. Legal sign-off on disclaimer text. Non-optional gate before Phase 1B launch. | Phase 1B | P0 – Critical | Must Have | Compliance | Dev Team | N/A |  | Backlog |  |  | MUST complete before any patient-facing launch of Phase 1B.
OMV-066 | AI Health Insights | Medical advisor partnership | Engage a qualified medical professional (MBBS min; MD preferred) for ongoing knowledge base curation and insight accuracy validation. | Phase 1B | P0 – Critical | Must Have | Compliance | Dev Team | N/A |  | Backlog |  |  | Non-negotiable quality gate. No automated trust of raw PubMed.
OMV-067 | AI Health Insights | Lab value extractor — health_metrics table | Post-OCR step for LAB_REPORT documents. Regex + NLP extracts structured values (marker, value, unit, ref_range). Confidence gate: <80% marked UNVERIFIED, excluded from predictions. | Phase 1B | P0 – Critical | Must Have | Technical | Patient | Premium |  | Backlog |  | OMV-017, OMV-019 | ~200 standard lab markers, Indian naming conventions.
OMV-068 | AI Health Insights | Medical knowledge base — RAG with pgvector | Curated, embedded medical research from PubMed, IJMR, Lancet Digital Health, WHO, ICMR, ADA, AHA, ACC, KDIGO. Stored as vector embeddings in PostgreSQL (pgvector). Monthly automated ingestion + human review gate. | Phase 1B | P0 – Critical | Must Have | Technical | Dev Team | N/A |  | Backlog |  | OMV-040 | text-embedding-3-small or Claude embeddings.
OMV-069 | AI Health Insights | Health profile builder — trend detection & threshold comparison | Aggregates health_metrics over time per patient. Detects trends (rising HbA1c), compares to clinical thresholds, cross-marker analysis. Only uses VERIFIED confidence-gated values. | Phase 1B | P0 – Critical | Must Have | Technical | Patient | Premium |  | Backlog |  | OMV-067 | Outputs PatientRiskProfile JSON.
OMV-070 | AI Health Insights | Risk assessment engine — rule-based layer (Layer A) | Pre-coded clinical thresholds from established guidelines. Only flags that pass rule-based check proceed to LLM. Prevents LLM fabrication. | Phase 1B | P0 – Critical | Must Have | Technical | Patient | Premium |  | Backlog |  | OMV-069 | Diseases: Diabetes, Hypertension, Thyroid, Anemia, Vitamin D, B12, Cardiovascular, Kidney.
OMV-071 | AI Health Insights | Risk assessment engine — LLM + RAG layer (Layer B) | Claude API with RAG. Strict system prompt: not a doctor, only cite provided research, never say 'diagnosis', always recommend consulting a doctor. Output validated against InsightSchema before use. | Phase 1B | P0 – Critical | Must Have | Technical | Patient | Premium |  | Backlog |  | OMV-068, OMV-070 | Model: claude-sonnet-4-6. JSON schema validation before storage.
OMV-072 | AI Health Insights | Insight publisher — dedup, throttle, severity gate | Before delivering: dedup (same insight in last 90 days?), throttle (max 2/patient/month), severity gate (MEDIUM or HIGH only). LOW risk logged silently. | Phase 1B | P0 – Critical | Must Have | Technical | Patient | Premium |  | Backlog |  | OMV-071 | Prevents alert fatigue.
OMV-073 | AI Health Insights | Health Insights in-app delivery — push + dashboard card | Push notification: 'You have a new health insight'. In-app Health Insights tab with full card including evidence citations. Mandatory disclaimer on first view (cannot be dismissed without acknowledgment). | Phase 1B | P1 – High | Must Have | Feature | Patient | Premium |  | Backlog |  | OMV-072, OMV-035
OMV-074 | AI Health Insights | Doctor beta testing of insights before patient launch | Show generated insights to 5–10 doctors for accuracy validation during beta. Document false positive/negative rates. | Phase 1B | P0 – Critical | Must Have | Compliance | Dev Team | N/A |  | Backlog |  | OMV-071 | Internal accuracy audit. Establish pause thresholds.
OMV-075 | AI Health Insights | AI Health Insights — free teaser (1 insight per quarter) | One free insight per quarter for free-tier patients to demonstrate value before upgrading. | Phase 1B | P2 – Medium | Should Have | Feature | Patient | Free |  | Backlog |  | OMV-073 | Freemium hook for AI Insights.
OMV-076 | Platform | iOS app — Flutter | Extend existing Flutter codebase to iOS. App Store submission and compliance. | Phase 2 | P0 – Critical | Must Have | Feature | Patient / Doctor | Free | A18 | Backlog |  | OMV-039 | Flutter single codebase — iOS readiness built in from Phase 1.
OMV-077 | Platform | Progressive Web App (PWA) — patient-facing | PWA version of the patient interface for web browser access. | Phase 2 | P1 – High | Should Have | Feature | Patient | Free |  | Backlog
OMV-078 | Localisation | 9 additional regional languages — UI & OCR | Add Telugu, Tamil, Marathi, Bengali, Punjabi, Gujarati, Kannada, Malayalam, Assamese. i18n translation files + OCR languageHints expansion. | Phase 2 | P1 – High | Must Have | Feature | All Actors | Free | A16 | Backlog |  | OMV-058 | Total Phase 2: 11 languages. Architecture unchanged — only hint array grows.
OMV-079 | Localisation | Hindi query support — Natural Language Query Interface | Accept Hindi-language queries. Query parsing LLM handles Hindi natively. Marker synonyms include Hindi equivalents. Response in same language as query. | Phase 2 | P2 – Medium | Should Have | Feature | Patient / Doctor | Premium |  | Backlog |  | OMV-108, OMV-078
OMV-080 | ABHA Integration | Ayushman Bharat Health Account (ABHA) linking | Allow patients to link their ABHA ID to their OmniMedVault profile. ABDM guidelines compliance. | Phase 2 | P1 – High | Must Have | Feature | Patient | Free | A3 | Backlog |  |  | ABHA adoption growing; adds complexity — deferred from Phase 1.
OMV-081 | Lab Integration | Direct lab-to-platform structured report upload | Labs push structured lab reports directly to a patient's OmniMedVault account. Actor: Lab (FR). | Phase 2 | P1 – High | Should Have | Feature | Lab | Free | A13 | Backlog
OMV-082 | Infrastructure | Microservices extraction — OCR & Search services | Extract OCR and Search from modular monolith into independently deployed services. First step of microservices migration. | Phase 2 | P1 – High | Should Have | Technical | Dev Team | N/A | A19 | Backlog |  | OMV-039 | Code boundaries already exist in monolith. Migration is operational not a rewrite.
OMV-083 | Monetisation | Stripe subscription management — hospital self-serve billing | Stripe integration for monthly/annual hospital SaaS subscriptions. Self-serve upgrade/downgrade. Three tiers: Clinic / Hospital / Enterprise. | Phase 2 | P0 – Critical | Must Have | Feature | Hospital Admin | B2B |  | Backlog |  | OMV-057
OMV-084 | Monetisation | Stripe subscription — patient premium billing | Stripe integration for patient Premium subscription. Monthly + annual (discounted) plans. UPI + card support. | Phase 2 | P0 – Critical | Must Have | Feature | Patient | Premium |  | Backlog |  | OMV-056
OMV-085 | Platform | Offline mode — last-seen cache (read-only) | Mobile app caches last-seen patient records for read-only offline access. | Phase 2 | P2 – Medium | Should Have | Feature | Patient | Free | A8 | Backlog
OMV-086 | Hospital / Institution | Hospital analytics dashboard — prescription trends, common diagnoses | Doctor-level and institution-level analytics: prescription trends, most common diagnoses, patients served per doctor. | Phase 2 | P2 – Medium | Should Have | Feature | Hospital Admin | B2B |  | Backlog |  | OMV-033
OMV-087 | Infrastructure | Distributed tracing — AWS X-Ray / OpenTelemetry | Full trace of every request across microservices. Identifies latency bottlenecks. Errors traced to exact line of code. | Phase 2 | P1 – High | Should Have | Technical | Dev Team | N/A |  | Backlog |  | OMV-082
OMV-088 | Infrastructure | Prometheus + Grafana — metrics dashboards | Service-level metrics (request rate, error rate, latency p50/95/99), business metrics (uploads/hr, OCR success rate, consents), infra metrics. | Phase 2 | P1 – High | Should Have | Technical | Dev Team | N/A |  | Backlog
OMV-089 | Infrastructure | Kubernetes (AWS EKS) migration | Migrate from ECS Fargate to EKS. Namespaces per service, HPA, Pod Disruption Budgets, Istio service mesh (mTLS), ArgoCD GitOps. | Phase 2 | P1 – High | Must Have | Technical | Dev Team | N/A |  | Backlog |  | OMV-082 | Enables full microservices operation.
OMV-090 | SOS Emergency | SOS trigger — press & hold 3 seconds UI | Always-visible SOS button on home screen. Press-and-hold 3 seconds triggers. Haptic feedback. 5-second cancel window post-trigger. | Phase 2 | P0 – Critical | Must Have | Feature | Patient | Free |  | Backlog |  |  | One-tap to trigger design constraint. FR: Section 23.
OMV-091 | SOS Emergency | SOS recipient identification — treating doctors, hospitals, nearest hospitals, emergency contacts | Identify recipients in priority order: (1) last 3 treating doctors (last 12 months), (2) active consultation hospitals, (3) 3 nearest hospitals via Google Places API within 5km, (4) patient-configured emergency contacts. | Phase 2 | P0 – Critical | Must Have | Feature | Patient | Free |  | Backlog |  | OMV-090
OMV-092 | SOS Emergency | SOS multi-channel alert delivery — push + SMS in parallel | Push (Firebase FCM high-priority channel) + SMS (Twilio/AWS SNS) sent simultaneously to all recipients. Total response time <2 seconds. | Phase 2 | P0 – Critical | Must Have | Technical | Patient | Free |  | Backlog |  | OMV-091, OMV-035, OMV-036
OMV-093 | SOS Emergency | Emergency profile URL — time-limited, login-free | On SOS trigger: generate a 4-hour public URL (https://omnimedvault.com/e/{random-12-char-token}). Shows blood group, allergies, active medications, last doctor, emergency contact. No full history. Sent to all recipients. | Phase 2 | P0 – Critical | Must Have | Feature | Patient | Free |  | Backlog |  | OMV-090 | Token is single-use, non-guessable. Same concept as Emergency QR but dynamically generated.
OMV-094 | SOS Emergency | Patient emergency contacts configuration — up to 3 contacts | Patient pre-configures 1–3 emergency contacts (name + phone + relation) in their profile. Priority ordered. | Phase 2 | P1 – High | Must Have | Feature | Patient | Free |  | Backlog |  |  | SMS + future WhatsApp Business API.
OMV-095 | SOS Emergency | SOS dashboard — doctor/hospital real-time acknowledgement | Doctors and hospitals see active SOS events in real-time in their app. Can tap 'I'm responding'. Patient sees acknowledgements on their screen. | Phase 2 | P1 – High | Must Have | Feature | Doctor / Hospital Admin | Free |  | Backlog |  | OMV-090
OMV-096 | SOS Emergency | SOS data model — sos_events, sos_recipients, patient_emergency_contacts | DB schema for SOS feature. Tables: sos_events, sos_recipients, patient_emergency_contacts. | Phase 2 | P0 – Critical | Must Have | Technical | Dev Team | N/A |  | Backlog |  | OMV-040
OMV-097 | SOS Emergency | SOS edge case handling — no GPS, no internet, accidental press, no doctors | Handle: no GPS (use last known + label), no internet (show 'Call 108' message + auto-open dialler), accidental press (5-sec cancel), no doctors in last 12 months (skip Priority 1), no hospitals within 5km (expand to 10km). | Phase 2 | P1 – High | Must Have | Technical | Dev Team | N/A |  | Backlog |  | OMV-090
OMV-098 | SOS Emergency | SOS covers all family members in group | SOS feature covers all family members in the same family account group. | Phase 2 | P2 – Medium | Should Have | Feature | Patient | Premium |  | Backlog |  | OMV-090, OMV-099
OMV-099 | Family Accounts | Family account — add managed dependents (no smartphone / elderly / child) | Primary account holder creates and fully manages a dependent profile: upload records, view full history. No smartphone required for dependent. | Phase 2 | P1 – High | Must Have | Feature | Patient | Premium | FR25, FR26 | Backlog |  |  | Child account: stays managed until manually converted or dependent claims own account.
OMV-100 | Family Accounts | Family account — add linked dependents (own OmniMedVault account) | Linked dependent has own account. Grants primary holder view of financial summary only. Medical records remain private. | Phase 2 | P1 – High | Must Have | Feature | Patient | Premium | FR26 | Backlog |  |  | Privacy rule enforced at data layer, not just UI.
OMV-101 | Family Accounts | Family financial dashboard — aggregated spend across all family members | Aggregated medical spend across all family members. Filterable per member. | Phase 2 | P2 – Medium | Should Have | Feature | Patient | Premium | FR27 | Backlog |  | OMV-099, OMV-100
OMV-102 | Family Accounts | Family account — data model (family_members table) | DB schema: family_members table with member_type (MANAGED / LINKED), financial_share_consent, relation. | Phase 2 | P1 – High | Must Have | Technical | Dev Team | N/A | FR25 | Backlog |  | OMV-040
OMV-103 | Family Medical Proxy | Proxy access request — initiation by proxy | Proxy sends access request to patient (phone number or OmniMedVault ID). Writes optional reason message. POST /family-proxy/request. | Phase 2 | P1 – High | Must Have | Feature | Patient / Proxy | Premium | FR35 | Backlog |  |  | Proxy must have Premium subscription to request access.
OMV-104 | Family Medical Proxy | Proxy consent lifecycle — approve / decline / revoke / expiry | Patient approves with: permanent / time-limited (7/30/90 days/custom) / single-use (24hr). Can revoke at any time with immediate effect. 3-day expiry warning notification. | Phase 2 | P1 – High | Must Have | Feature | Patient | Premium | FR37 | Backlog |  | OMV-103
OMV-105 | Family Medical Proxy | Proxy read-only access — timeline, documents, search, active meds | Proxy can view: full medical timeline, search records, active medications/allergies card, download PDFs, share documents externally. Cannot upload, edit, delete, or prescribe. | Phase 2 | P1 – High | Must Have | Feature | Proxy | Premium | FR36 | Backlog |  | OMV-104
OMV-106 | Family Medical Proxy | Proxy access audit — every access triggers patient push notification | Every proxy record access generates audit log entry (actor_role=FAMILY_PROXY) and push notification to patient. Consolidated notification for multiple views within 30 minutes. | Phase 2 | P0 – Critical | Must Have | Compliance | Patient | Premium | FR38 | Backlog |  | OMV-104, OMV-014
OMV-107 | Family Medical Proxy | Proxy data model — family_medical_proxies table | DB schema: family_medical_proxies table with status enum (PENDING/ACTIVE/DECLINED/EXPIRED/REVOKED), expires_at, relation, request_message. | Phase 2 | P1 – High | Must Have | Technical | Dev Team | N/A | FR35 | Backlog |  | OMV-040 | Constraint: no sub-delegation. Proxy cannot grant access to others.
OMV-108 | NL Query Interface | Query parsing — LLM-based intent & entity extraction | Single LLM call parses raw query text into structured JSON: intent, marker, date_range, fallback_range_months. Handles informal terms, abbreviations, mixed language. | Phase 2 | P1 – High | Must Have | Technical | Patient / Doctor | Premium | FR40 | Backlog
OMV-109 | NL Query Interface | Primary deterministic query — health_metrics & records lookup | Deterministic DB query against health_metrics using structured output from parser. No LLM in this step. Exact match check. | Phase 2 | P1 – High | Must Have | Technical | Patient / Doctor | Premium | FR41 | Backlog |  | OMV-108
OMV-110 | NL Query Interface | Fallback — temporal range expansion (±6 months) | If no exact match: expand query window ±6 months. Return up to 3 records sorted by proximity to requested date. Flag fallback_used=true. Never interpolate or estimate values. | Phase 2 | P1 – High | Must Have | Technical | Patient / Doctor | Premium | FR42 | Backlog |  | OMV-109 | ±6 months configurable per marker type in future enhancement.
OMV-111 | NL Query Interface | Grounded response generation — second LLM call | Second LLM call formats retrieved records as human-readable answer. Strict system prompt: format only retrieved data, no additions, no advice, no diagnosis. | Phase 2 | P1 – High | Must Have | Technical | Patient / Doctor | Premium | FR41, FR42 | Backlog |  | OMV-109, OMV-110
OMV-112 | NL Query Interface | Marker synonym resolution lookup table | Curated table mapping informal query terms to canonical marker names. Examples: 'HB' → 'Hemoglobin', 'sugar' → Fasting Glucose + HbA1c, 'thyroid' → TSH + T3 + T4. | Phase 2 | P2 – Medium | Must Have | Technical | Dev Team | N/A | FR44 | Backlog |  |  | Extended over time as query logs reveal new informal terms.
OMV-113 | NL Query Interface | Trend query — scatter chart with straight-line segments | Trend queries display a scatter plot with straight-line segments connecting actual data points. Dashed segments for gaps >180 days. Every point tappable to source document. No smooth curves, no regression lines, no projections. | Phase 2 | P2 – Medium | Must Have | Feature | Patient / Doctor | Premium | FR44 | Backlog |  | OMV-111 | Graph only for 2+ records. Toggle between graph and text view.
OMV-114 | NL Query Interface | Doctor query interface — consent check + audit + patient notification | Doctor queries patient records via NL interface. Mandatory consent check before any data. Every query audited (actor_role=DOCTOR). Patient push notification per query session. | Phase 2 | P1 – High | Must Have | Compliance | Doctor | Free | FR43 | Backlog |  | OMV-012, OMV-108 | Doctor NL query is included in all hospital tiers — not a premium upsell.
OMV-115 | NL Query Interface | Query history — last 50 queries with re-run button | Last 50 queries accessible in-app. Shows: query text, one-line response preview, date/time, Re-run button. Personal per user (patient vs doctor vs proxy). | Phase 2 | P2 – Medium | Should Have | Feature | Patient / Doctor | Premium | FR45 | Backlog |  | OMV-111
OMV-116 | NL Query Interface | NL query data model — nl_queries INSERT-only table | DB schema: nl_queries table. INSERT-only, never updated or deleted. Logs: query text (encrypted), detected_intent, extracted_entities, result_found, fallback_used, response_text (encrypted), latency_ms. | Phase 2 | P1 – High | Must Have | Technical | Dev Team | N/A | FR45 | Backlog |  | OMV-040
OMV-117 | Phase 3 — Ecosystem | Pharmacy integration — verify & dispense against digital prescriptions | Pharmacies can verify and dispense against OmniMedVault digital prescriptions. Low priority per Assumption A12. | Phase 3 | P3 – Low | Could Have | Feature | Lab / Pharmacy | B2B | A12 | Backlog |  |  | Requires pharmacy network partnerships.
OMV-118 | Phase 3 — Ecosystem | Full microservices migration | Complete extraction of all services from monolith into independently deployed microservices. Kafka event bus throughout. Istio service mesh. | Phase 3 | P2 – Medium | Should Have | Technical | Dev Team | N/A |  | Backlog |  | OMV-082, OMV-089
OMV-119 | Phase 3 — Ecosystem | AI-driven drug interaction warnings | Detect potential drug interactions across a patient's active prescriptions. Requires full pharmacy database and regulatory review. | Phase 3 | P2 – Medium | Could Have | Feature | Patient / Doctor | Premium |  | Backlog |  | OMV-117 | Regulatory complexity. Separate feature from AI Health Insights.
OMV-120 | Phase 3 — Ecosystem | Direct integration with major hospital HIS (hospital information systems) | Pre-built integrations with specific HIS vendors (beyond generic REST API + widget). | Phase 3 | P2 – Medium | Could Have | Feature | Hospital Admin | B2B |  | Backlog |  | OMV-032 | Requires bilateral agreements with HIS vendors.
OMV-121 | Phase 3 — Ecosystem | Telemedicine referral handoff | OmniMedVault doctor can refer a patient to a telemedicine provider, passing relevant medical context. | Phase 3 | P3 – Low | Could Have | Feature | Doctor | B2B |  | Backlog |  |  | Telemedicine (video/audio consultation) is out of scope per A11.
OMV-122 | Phase 3 — Ecosystem | General Wellness Tips — geo-customised content from global journals | Geo-customised wellness content sourced from global wellness journals, tailored to patient's geographical location (country, state, region). Completely separate from medical history feature set. Detail design deferred to Phase 3 planning. | Phase 3 | P3 – Low | Could Have | Feature | Patient | Free / Premium |  | Backlog |  |  | A tip valid in Punjab may not apply in Kerala. See memory: project_phase3_wellness_tips.md.
OMV-123 | Phase 3 — Ecosystem | WhatsApp Business API — SOS emergency contact delivery | Extend SOS emergency contact delivery to WhatsApp Business API in addition to SMS. | Phase 3 | P3 – Low | Could Have | Feature | Patient | Free |  | Backlog |  | OMV-092
OMV-124 | Monthly Health Intelligence Journal | Journal data aggregation pipeline — anonymised health trends by geography, age, medicine | Aggregate anonymised patient data by: Geography × Season (disease prevalence), Age Group × Condition, Geography × Medicine/Active Salt. Differential privacy / k-anonymity required. Minimum cohort guardrail before any stat published. | Future | P3 – Low | Won't Have | Feature | Dev Team | B2B / B2G |  | Backlog |  |  | GATE: requires ~1yr of production data from a substantial user base. Do not start earlier.
OMV-125 | Monthly Health Intelligence Journal | Patient opt-in consent for commercial intelligence use of anonymised data | Separate consent for anonymised data to be used in commercial health intelligence publications. Distinct from core product consent. DPDPA 2023 + GDPR compliant. | Future | P3 – Low | Won't Have | Compliance | Patient | N/A |  | Backlog |  | OMV-124 | Legal review required before any data commercialisation.
OMV-126 | Monthly Health Intelligence Journal | Developer-only journal publisher — internal portal with review & approval | Role-gated internal admin portal. Only OmniMedVault developers can access, review, and publish journal editions. Audit log of who reviewed/published each edition. No automated publishing. | Future | P3 – Low | Won't Have | Feature | Dev Team | N/A |  | Backlog |  | OMV-124 | Format TBD: PDF / internal dashboard / structured API export.
OMV-127 | Monthly Health Intelligence Journal | B2B / B2G commercialisation — pharma, government health bodies, insurers | Sell journal insights and anonymised datasets to: pharma companies (regional demand forecasting), government health bodies (public health schemes), health insurers, NGOs, research institutions. | Future | P3 – Low | Won't Have | Feature | Dev Team | B2B / B2G |  | Backlog |  | OMV-126 | Positions OmniMedVault as a Public Health Intelligence platform. New revenue stream.
OMV-128 | NL Query Interface | Configurable fallback window per marker type | NL Query fallback window (±6 months default) made configurable per marker type. Faster-moving markers (infection) get tighter window; lifestyle markers get wider window. | Future | P3 – Low | Could Have | Technical | Dev Team | N/A | FR42 | Backlog |  | OMV-110 | Future enhancement — not required for Phase 2 launch.

## Legend
OmniMedVault Backlog — Legend & Guide
PHASE / RELEASE
Phase 1A | Core product (months 1–6): patient/doctor/hospital core, OCR, search, Financial Tracking (Premium).
Phase 1B | AI Health Insights (months 5–8): lab value extraction, risk engine, RAG medical knowledge base.
Phase 2 | Scale & Ecosystem (months 9–18): iOS, 9 languages, ABHA, SOS, Family Accounts, Medical Proxy, NL Query.
Phase 3 | Ecosystem Completion (18+ months): pharmacy, full microservices, drug interactions, HIS, telemedicine.
Future | Unscheduled — requires ~1yr production data. Monthly Health Intelligence Journal, B2B/B2G data commercialisation.
PRIORITY
P0 – Critical | Blocker — must be resolved before related items can progress. Launch-critical.
P1 – High | High importance — in scope for the current phase. Ship with it.
P2 – Medium | Meaningful value — include if capacity allows in the phase.
P3 – Low | Nice-to-have — defer to a later phase without significant impact.
MoSCoW
Must Have | Non-negotiable. Phase fails without this.
Should Have | High value; included unless a hard constraint prevents it.
Could Have | Nice-to-have. Included only if time and capacity allow.
Won't Have | Explicitly out of scope for this phase (may be revisited later).
STATUS
Backlog | Accepted into backlog; not yet prioritised into a sprint.
Ready | Refined, estimated, and ready to pull into a sprint.
In Progress | Actively being worked on.
Done | Implemented, reviewed, and merged.
Blocked | Cannot progress — dependency or blocker unresolved.
On Hold | Paused intentionally (e.g., waiting for external sign-off).
SUBSCRIPTION TIER
Free | Available to all patients on the free tier.
Premium | Patient Premium subscription required.
B2B | Hospital/clinic subscription (B2B SaaS).
B2B/B2G | Business-to-business or business-to-government (future journal feature).
N/A | Internal / infrastructure — not user-facing.
COLUMNS GUIDE
ID | Unique backlog item identifier. Format: OMV-NNN.
Epic | High-level feature grouping.
Feature / Story | Concise user-facing or developer-facing deliverable.
Description | What needs to be built and key constraints.
Phase | Target release phase.
Priority | P0–P3 priority level.
MoSCoW | Must / Should / Could / Won't Have classification.
Category | Feature / Technical / Compliance / Security / Infrastructure.
Actor | Primary user role(s) impacted.
Subscription | Free / Premium / B2B / N/A.
FR Ref | Functional requirement reference from SYSTEM_DESIGN.md.
Status | Current workflow state.
Story Points | Effort estimate (fill during sprint planning).
Dependencies | OMV-IDs this item depends on.
Notes | Additional context, constraints, open questions.
Owner | Developer / team assigned (fill during sprint planning).
Sprint / Milestone | Sprint number or milestone name (fill during sprint planning).

## Phase Summary
OmniMedVault — Phase Delivery Summary
Phase | Items | Priority Breakdown | Key Deliverables (sample)
Phase 1A | 64 | P0: 42 ¦ P1: 18 ¦ P2: 4 | Core product: Patient & Doctor mobile app, OCR pipeline, search, consent/audit, CRM widget, Hospital admin, Financial Tracking (Premium receipt parsing + illness episodes + expense reports), Emergency QR, CI/CD, security baseline.
Phase 1B | 11 | P0: 9 ¦ P1: 1 ¦ P2: 1 | AI Health Insights engine: lab value extraction, rule-based + LLM risk assessment, RAG medical knowledge base (PubMed/ICMR/WHO/ADA), InsightSchema delivery. CDSCO regulatory review mandatory gate.
Phase 2 | 41 | P0: 9 ¦ P1: 24 ¦ P2: 8 | iOS app, 9 regional languages, ABHA integration, lab direct upload, SOS Emergency feature, Family Accounts (managed/linked dependents), Family Medical Proxy, Natural Language Query Interface (patient + doctor), Stripe billing, microservices extraction.
Phase 3 | 7 | P2: 3 ¦ P3: 4 | Pharmacy integration, full microservices migration, AI drug interaction warnings, direct HIS vendor integrations, telemedicine referral handoff, General Wellness Tips (geo-customised).
Future | 5 | P3: 5 | Monthly Health Intelligence Journal (requires ~1yr production data): anonymised health trend aggregation by geography/age/medicine. B2B/B2G commercialisation to pharma, government, insurers. Strict anonymisation, patient opt-in consent, regulatory review.